|  |  |
| --- | --- |
| July-Sept 2023 | Obtain the limited use NH-CHIS data. Descriptive analysis and visualization for establishing stylized facts about telemedicine before, during/after the COVID pandemic. We apply for the use of the BC data. |
| Oct-Dec 2023 | Regression analysis to exam how the introduction of telemedicines affected the frequency of ordering diagnostic lab/imaging and eventual health outcomes as described in the detailed proposal using the NH-CHIS data. We conduct descriptive analysis using the BC data. |
| Jan-Mar 2024 | The first draft of a paper on the effect of telemedicines on initial diagnosis and health outcomes using the NH-CHIS data. We also prepare a reproducible code that will be publicly available. |
| Apr-June 2024 | The second draft of a paper on the effect of telemedicines on initial diagnosis and health outcomes using the NH-CHIS data. Submission to conferences. Regression analysis using the BC data. |
| July-Sept 2024 | The third draft of a paper on the effect of telemedicines on initial diagnosis and health outcomes using the NH-CHIS data. We will present the paper at internal workshops as well as external seminars. Submission to conferences. The first draft of the paper using the BC data. |
| Oct-Dec 2024 | The fourth draft of a paper on the effect of telemedicines using the NH-CHIS data. We will present the paper at external seminars/conferences to receive comments and revise the paper. Submission to conferences. The second draft of the paper using the BC data. |
| Jan-Mar 2025 | We will submit the paper using the NH-CHIS data to a journal (e.g., AEJ: economic policy, Journal of Public Economics, Journal of Health Economics). The third draft of a paper on the effect of telemedicines using the BC data. Submission to conferences. |
| Apr-June 2025 | The fourth draft of a paper on the effect of telemedicines using the BC data. We will present the paper at internal workshops as well as external seminars. |
| July 2025- | The final draft of a paper on the effect of telemedicines using the BC data. Submission to a journal. |

**Timeline for conducting the proposed project (July 2023 – June 2025)**